WEEK 2 PROJECT REPORT

Detailed Project Plan for an E-Commerce Platform

Project Planning & Management | Week 2

| Document Item | Details |
| --- | --- |
| Project | Scalable E-Commerce Platform |
| Task | Week 2 – Develop a Detailed Project Plan |
| Planned Duration | 12 weeks |
| Primary Deliverable | Production-ready e-commerce platform |
| Prepared By | Software Development Intern |

# 1. Project Overview

The project is the implementation of a scalable e-commerce platform based on the requirements and architecture established during Week 1. The platform will provide customers with a secure and convenient way to register, browse products, manage a shopping cart, place orders, and complete payments. The plan coordinates software development, quality assurance, security, deployment, and documentation activities.

## 1.1 Project Objectives

Implement the approved functional requirements and system architecture.

Develop secure user authentication, product catalog, cart, order, and payment capabilities.

Provide a responsive and user-friendly web interface.

Integrate backend services through well-defined APIs.

Validate functionality, performance, reliability, and security before release.

Deploy the application using a repeatable and monitored production process.

## 1.2 Scope

In scope:

User registration, login, authentication, and basic profile management.

Product catalog, categories, product details, and search/filter support.

Shopping cart, order creation, order status, and checkout.

Payment gateway integration using a secure third-party provider.

Frontend web application and backend APIs/services.

Automated testing, security validation, deployment, monitoring, and documentation.

Out of scope for the initial release:

Native mobile applications.

Advanced recommendation/AI personalization.

International tax and multi-currency expansion beyond the approved release scope.

Complex seller marketplace functionality.

# 2. Detailed Task Breakdown

The work is divided into sequential and overlapping phases. Development tasks are started after the main architecture is approved, while testing and documentation continue throughout the later stages.

| ID | Task | Phase | Start | End | Key Output |
| --- | --- | --- | --- | --- | --- |
| T01 | Project initiation & requirements | Planning | W1 | W5 | Approved scope and backlog |
| T02 | Architecture & database design | Design | W2 | W5 | Architecture and schema |
| T03 | UI/UX design | Design | W2 | W5 | Wireframes and UI prototype |
| T04 | User authentication service | Development | W3 | W7 | Authentication APIs |
| T05 | Product catalog service | Development | W3 | W7 | Catalog APIs |
| T06 | Cart & order service | Development | W5 | W7 | Cart/order APIs |
| T07 | Payment integration | Development | W6 | W7 | Payment workflow |
| T08 | Frontend implementation | Development | W4 | W9 | Responsive web interface |
| T09 | API/system integration | Integration | W8 | W10 | Integrated application |
| T10 | Testing & security validation | Testing | W9 | W11 | Validated release candidate |
| T11 | Deployment & production setup | Deployment | W11 | W12 | Production deployment |
| T12 | Documentation & handover | Closure | W11 | W12 | Technical/user documentation |

## 2.1 Work Breakdown Structure

| WBS | Work Package | Activities |
| --- | --- | --- |
| 1.0 | Project Management | Planning, status tracking, stakeholder communication |
| 2.0 | Requirements & Design | Requirements baseline, architecture, database, UI/UX |
| 3.0 | Backend Development | Authentication, catalog, cart/order, payment |
| 4.0 | Frontend Development | Pages, forms, product views, cart and checkout |
| 5.0 | Integration & Testing | API integration, functional, security and performance tests |
| 6.0 | Deployment | CI/CD, infrastructure, monitoring and production release |
| 7.0 | Closure | Documentation, knowledge transfer and final handover |

# 3. Resource Allocation Plan

The plan uses a small cross-functional team. Some specialist roles are part-time because their highest-value activities occur during specific project phases.

| Role | Allocation | Primary Responsibilities |
| --- | --- | --- |
| Project Manager | 1 FTE | Planning, coordination, schedule, risks, reporting |
| Backend Developer | 2 FTE | APIs, services, database integration, business logic |
| Frontend Developer | 1 FTE | Web UI, forms, state handling, frontend/API integration |
| UI/UX Designer | 1 FTE | Wireframes, prototype, usability and design consistency |
| QA Engineer | 1 FTE | Test planning, functional, regression and integration testing |
| DevOps Engineer | 1 FTE | CI/CD, environments, deployment and monitoring |
| Security Specialist | 0.5 FTE | Security review, vulnerability assessment and guidance |

## 3.1 Tools and Infrastructure

| Area | Planned Tools/Technology | Purpose |
| --- | --- | --- |
| Source Control | Git + GitHub | Version control, pull requests and collaboration |
| Backend | Python/REST APIs | Business logic and service endpoints |
| Frontend | HTML/CSS/JavaScript or approved framework | Customer-facing web interface |
| Database | PostgreSQL | Persistent transactional data |
| Testing | Pytest + API/browser testing tools | Automated and manual validation |
| CI/CD | GitHub Actions or equivalent | Automated build and test pipeline |
| Deployment | Cloud environment + containers | Repeatable application deployment |
| Monitoring | Logs, metrics and alerts | Operational visibility |

# 4. Project Timeline and Milestones

The schedule is planned for 12 weeks. Tasks overlap where practical to reduce idle time, while milestone reviews provide decision points before major transitions.

| Milestone | Target | Acceptance Criteria |
| --- | --- | --- |
| M1 – Requirements approved | Week 1 | Scope, priorities and requirements baseline approved |
| M2 – Architecture approved | Week 2 | Architecture, database approach and technical risks reviewed |
| M3 – Core services ready | Week 7 | Authentication, catalog, cart/order and payment components available |
| M4 – Feature-complete build | Week 9 | Main frontend and backend features integrated |
| M5 – Testing sign-off | Week 11 | Critical defects resolved; release candidate approved |
| M6 – Production release | Week 12 | Deployment completed and handover accepted |

## 4.1 Weekly Schedule

| Week | Main Activities | Expected Result |
| --- | --- | --- |
| 1 | Initiation, requirements, backlog | Requirements baseline |
| 2 | Architecture, database, UI/UX start | Architecture review |
| 3 | Authentication + catalog development | Core APIs started |
| 4 | Backend development + frontend foundation | Working development build |
| 5 | Cart/order development + UI/UX completion | Checkout flow design |
| 6 | Payment integration + frontend features | Payment sandbox flow |
| 7 | Core service completion | Core services milestone |
| 8 | Frontend/API integration | Integrated test build |
| 9 | Feature completion + test preparation | Feature-complete build |
| 10 | Integration, functional and performance testing | Defect resolution |
| 11 | Security testing, regression, deployment preparation | Testing sign-off |
| 12 | Production deployment, monitoring and handover | Production release |

## 4.2 High-Level Gantt View

Legend: ■ = active work period; spacing represents later project weeks.

| Workstream | Schedule Indicator |
| --- | --- |
| Requirements & Planning | ■■■■■■ |
| Architecture & Design | ■■■■ |
| Backend Development | ■■■■■■■ |
| Frontend Development | ■■■■■■■ |
| Integration | ■■■ |
| Testing & Security | ■■■ |
| Deployment & Handover | ■■ |

# 5. Risk Management Plan

Risk management will be continuous throughout the project. Risks are reviewed during weekly status meetings and escalated when their probability or impact increases.

| ID | Risk | Probability | Impact | Mitigation / Response |
| --- | --- | --- | --- | --- |
| R1 | Requirements changes | Medium | High | Baseline requirements; use change requests and impact analysis. |
| R2 | Payment/API failure | Medium | High | Sandbox tests, timeouts, retries and clear failure handling. |
| R3 | Security vulnerability | Medium | Very High | Secure coding, dependency scanning, authentication controls and security tests. |
| R4 | Schedule delay | Medium | High | Track critical path, prioritize blockers and maintain contingency. |
| R5 | Performance/scalability issues | Medium | High | Load-test APIs; optimize queries, caching and infrastructure. |
| R6 | Data loss/corruption | Low | Very High | Automated backups, constraints, recovery testing and monitoring. |
| R7 | Integration defects | Medium | Medium | API contracts, integration tests and early end-to-end testing. |
| R8 | Deployment failure | Low | High | CI/CD, staging environment, deployment checklist and rollback plan. |

## 5.1 Risk Response Strategy

Identify: Record new technical, schedule, resource, security, and dependency risks.

Assess: Rate probability and impact using Low/Medium/High/Very High categories.

Mitigate: Assign an owner and implement preventive controls before the risk occurs.

Monitor: Review risk status during weekly project meetings.

Respond: Execute contingency or rollback actions when a risk becomes an issue.

# 6. Quality, Communication and Project Control

| Control Area | Approach |
| --- | --- |
| Quality | Code reviews, automated tests, integration testing and release checklist |
| Schedule | Weekly progress tracking against tasks and milestones |
| Scope | Approved requirements baseline and controlled change requests |
| Communication | Weekly team meeting plus milestone review meetings |
| Defects | Prioritized defect backlog with severity and owner |
| Security | Secure development practices and security validation before release |
| Deployment | Staging validation, automated pipeline and rollback procedure |

# 7. Project Success Criteria

All approved critical and high-priority functional requirements are implemented.

Core customer workflows—registration, product browsing, cart, checkout, payment, and order handling—work end to end.

Critical security and data-integrity issues are resolved before production release.

The release candidate passes functional, integration, regression, and agreed performance tests.

Production deployment is completed with monitoring, documentation, and a rollback plan.

Stakeholders accept the final system and project documentation.

# 8. Conclusion

This 12-week project plan provides a realistic roadmap for implementing the e-commerce platform defined in Week 1. It connects tasks, people, technology, milestones, and risk controls so that development can be tracked from requirements through production release. The plan also provides clear checkpoints for reviewing scope, quality, schedule, and security, helping the team identify problems early and deliver the platform in a controlled manner.

# Appendix A – Planning Assumptions

The Week 1 requirements and architecture are available and approved before full development begins.

Team members are available according to the resource allocation plan.

Third-party payment and cloud services provide development/sandbox access.

The initial release targets a web-based customer experience.

The 12-week timeline is an estimated baseline and may be revised through controlled change management.